## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2018-07-15 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28
|  |  |  | 160 | 148 | 136 | 124 | 112 | 100 | 88 | 76 | 64 | 52 | 40 | 28 | 16 | 4 | Ideal Burndown
|  |  | 160 | 158 | 152 | 140 | 123 | 113 | 103 | 96 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | Remaining Hrs (Total)
Enable Add Card API to allows users to add and manage starbucks cash cards | Design Business Logic | Harini Balakrishnan | 10 | 2018-07-15: 10; 2018-07-16: 9; 2018-07-17: 7; 2018-07-18: 4; 2018-07-19: 4; 2018-07-20: 2; 2018-07-21: 2; 2018-07-22: 0
| Design User Interface | Harini Balakrishnan | 2 | 2018-07-15: 2; 2018-07-16: 2; 2018-07-17: 2; 2018-07-18: 1; 2018-07-19: 1; 2018-07-20: 1; 2018-07-21: 1; 2018-07-22: 1
| Implement Back-End Code | Harini Balakrishnan | 15 | 2018-07-15: 15; 2018-07-16: 15; 2018-07-17: 15; 2018-07-18: 12; 2018-07-19: 12; 2018-07-20: 10; 2018-07-21: 9; 2018-07-22: 9
| Implement Front-End Code | Harini Balakrishnan | 3 | 2018-07-15: 3; 2018-07-16: 3; 2018-07-17: 3; 2018-07-18: 3; 2018-07-19: 3; 2018-07-20: 3; 2018-07-21: 3; 2018-07-22: 3
| Complete Unit Testing | Harini Balakrishnan | 2 | 2018-07-15: 2; 2018-07-16: 2; 2018-07-17: 2; 2018-07-18: 2; 2018-07-19: 1; 2018-07-20: 1; 2018-07-21: 1; 2018-07-22: 0
| Complete Regression Testing | Harini Balakrishnan | 5 | 2018-07-15: 5; 2018-07-16: 5; 2018-07-17: 5; 2018-07-18: 5; 2018-07-19: 4; 2018-07-20: 4; 2018-07-21: 4; 2018-07-22: 4
| Write Documentation | Harini Balakrishnan | 3 | 2018-07-15: 3; 2018-07-16: 3; 2018-07-17: 3; 2018-07-18: 3; 2018-07-19: 3; 2018-07-20: 2; 2018-07-21: 2; 2018-07-22: 2
Enable Managed Order API to allow users to select items from the menu and place an order | Design Business Logic | Ravali Nagabandi | 10 | 2018-07-15: 10; 2018-07-16: 9; 2018-07-17: 7; 2018-07-18: 4; 2018-07-19: 4; 2018-07-20: 2; 2018-07-21: 2; 2018-07-22: 0
| Design User Interface | Ravali Nagabandi | 2 | 2018-07-15: 2; 2018-07-16: 2; 2018-07-17: 2; 2018-07-18: 1; 2018-07-19: 1; 2018-07-20: 1; 2018-07-21: 1; 2018-07-22: 1
| Implement Back-End Code | Ravali Nagabandi | 15 | 2018-07-15: 15; 2018-07-16: 15; 2018-07-17: 14; 2018-07-18: 11; 2018-07-19: 10; 2018-07-20: 10; 2018-07-21: 9; 2018-07-22: 9
| Implement Front-End Code | Ravali Nagabandi | 3 | 2018-07-15: 3; 2018-07-16: 3; 2018-07-17: 3; 2018-07-18: 3; 2018-07-19: 2; 2018-07-20: 2; 2018-07-21: 2; 2018-07-22: 2
| Complete Unit Testing | Ravali Nagabandi | 2 | 2018-07-15: 2; 2018-07-16: 2; 2018-07-17: 2; 2018-07-18: 2; 2018-07-19: 1; 2018-07-20: 1; 2018-07-21: 1; 2018-07-22: 0
| Complete Regression Testing | Ravali Nagabandi | 5 | 2018-07-15: 5; 2018-07-16: 5; 2018-07-17: 5; 2018-07-18: 5; 2018-07-19: 4; 2018-07-20: 4; 2018-07-21: 3; 2018-07-22: 3
| Write Documentation | Ravali Nagabandi | 3 | 2018-07-15: 3; 2018-07-16: 3; 2018-07-17: 3; 2018-07-18: 3; 2018-07-19: 3; 2018-07-20: 2; 2018-07-21: 2; 2018-07-22: 2
Enable user authentication API to create a new account and succesful login with the newly created credentials | Design Business Logic | Rupal Martin | 5 | 2018-07-15: 4; 2018-07-16: 3; 2018-07-17: 1; 2018-07-18: 1; 2018-07-19: 1; 2018-07-20: 1; 2018-07-21: 1; 2018-07-22: 1
| Design User Interface | Rupal Martin | 3 | 2018-07-15: 3; 2018-07-16: 3; 2018-07-17: 3; 2018-07-18: 3; 2018-07-19: 3; 2018-07-20: 3; 2018-07-21: 3; 2018-07-22: 3
| Implement Back-End Code | Rupal Martin | 10 | 2018-07-15: 9; 2018-07-16: 8; 2018-07-17: 7; 2018-07-18: 6; 2018-07-19: 5; 2018-07-20: 4; 2018-07-21: 3; 2018-07-22: 3
| Implement Front-End Code | Rupal Martin | 8 | 2018-07-15: 8; 2018-07-16: 8; 2018-07-17: 8; 2018-07-18: 8; 2018-07-19: 7; 2018-07-20: 7; 2018-07-21: 7; 2018-07-22: 7
| Complete Unit Testing | Rupal Martin | 6 | 2018-07-15: 8; 2018-07-16: 8; 2018-07-17: 8; 2018-07-18: 7; 2018-07-19: 7; 2018-07-20: 7; 2018-07-21: 6; 2018-07-22: 6
| Complete Regression Testing | Rupal Martin | 2 | 2018-07-15: 2; 2018-07-16: 2; 2018-07-17: 2; 2018-07-18: 2; 2018-07-19: 2; 2018-07-20: 2; 2018-07-21: 2; 2018-07-22: 2
| Write Documentation | Rupal Martin | 6 | 2018-07-15: 5; 2018-07-16: 5; 2018-07-17: 5; 2018-07-18: 5; 2018-07-19: 5; 2018-07-20: 5; 2018-07-21: 5; 2018-07-22: 4
Implement Payment API for users to make Payment for their order using their registered card. | Design Business Logic | Supreetha Ganapathi | 5 | 2018-07-15: 4; 2018-07-16: 3; 2018-07-17: 1; 2018-07-18: 1; 2018-07-19: 1; 2018-07-20: 1; 2018-07-21: 1; 2018-07-22: 1
| Design User Interface | Supreetha Ganapathi | 3 | 2018-07-15: 3; 2018-07-16: 3; 2018-07-17: 3; 2018-07-18: 3; 2018-07-19: 3; 2018-07-20: 3; 2018-07-21: 3; 2018-07-22: 3
| Implement Back-End Code | Supreetha Ganapathi | 10 | 2018-07-15: 9; 2018-07-16: 8; 2018-07-17: 7; 2018-07-18: 6; 2018-07-19: 5; 2018-07-20: 4; 2018-07-21: 4; 2018-07-22: 4
| Implement Front-End Code | Supreetha Ganapathi | 8 | 2018-07-15: 8; 2018-07-16: 8; 2018-07-17: 8; 2018-07-18: 8; 2018-07-19: 8; 2018-07-20: 8; 2018-07-21: 7; 2018-07-22: 7
| Complete Unit Testing | Supreetha Ganapathi | 6 | 2018-07-15: 8; 2018-07-16: 8; 2018-07-17: 7; 2018-07-18: 7; 2018-07-19: 6; 2018-07-20: 6; 2018-07-21: 5; 2018-07-22: 5
| Complete Regression Testing | Supreetha Ganapathi | 2 | 2018-07-15: 2; 2018-07-16: 2; 2018-07-17: 2; 2018-07-18: 2; 2018-07-19: 2; 2018-07-20: 2; 2018-07-21: 2; 2018-07-22: 2
| Write Documentation | Supreetha Ganapathi | 6 | 2018-07-15: 5; 2018-07-16: 5; 2018-07-17: 5; 2018-07-18: 5; 2018-07-19: 5; 2018-07-20: 5; 2018-07-21: 5; 2018-07-22: 4
Merge the controller and test the REST services with application flow
Prepare for presentaion, documentation, demonstration PPT etc
Team:
Harini Balakrishnan | 20 hours / Week
Ravali Nagabandi | 20 hours / Week
Rupal Martin | 20 hours / Week
Supreetha Ganapathi | 20 hours / Week
Total Available Hours During Sprint: | 160 hours